## Slide 1
StoryStage 2 workplan: schedule
Earliest-start schedule from the dependency map, with about 8 parallel Claude Code sessions. Durations are estimates; re-plan as work is measured.
Critical path
First release
Owner-led
AR, projection, pathway
Nov 2026
Dec 2026
Jan 2027
Feb 2027
Mar 2027
Apr 2027
May 2027
w0
w2
w4
w6
w8
w10
w12
w14
w16
w18
w20
w22
w24
w26
w28
w30
Start: Mon 19 Oct 2026
Foundations, quality
WP0
WP0s
18b gate tests
WP18a
Spikes
WP1.1
WP1 spikes
1.11 classroom
Language, Story API
WP2 AST
WP6 runtime
4a API spec
4d
4b API blocks
Stage
5a stage core
5b extras
4c character actions
Backstage
WP3a
3b model pipelines
3c budgets
3i import, sketches
10s sketches
3d storybook cast (commissioned)
Interface
12a mock-ups
12b design system
10a Storyboard
WP7
10b links
WP10c
Tile editor
7c Tiles editor (C)
WP7t
Productions
9a
8f format
9b import
WP8 scenes, save
Screening room
WP11a
11b Screening room
WP11c
Prompter, speech
WP13a
14a speech
13b Prompter core
14b
WP13c
Apps
WP15a
15b signing, stores
24b class set-up
15k key
WP24a
Curriculum, legal, pilot
WP16a
16b templates
17b DPIA
WP19 pilot and editor study
WP17a
19a website, guide
AR
WP21 AR design mode
22b AR player
22c MR film
22a AR baker, pack
Projection
23a spike
23b Projection stage
23c class
23d Export to Pixera
Pathway
WP20 pathway: Unreal, Unity, Godot
Release candidate · 26 Feb 2027
Pilot ends · 9 Apr 2027
Critical path: repo and contracts → spikes → stage core → Story API blocks → Production stage (Blocks) → storyboard links and story coach → gate tests → release candidate → pilot and editor study.
Parallel sessions: 8 gives this schedule; 6 moves the release candidate about 4 weeks later; 4 about 13 weeks. AR, projection and the pathway start after the release candidate. Owner reviews, decisions and device runs set the real pace. Source: StoryStage2-workplan.md, section 5a.